# OpsFlow AI — Phase 2 Build Plan

Actionable engineering backlog derived from the Phase 2 Implementation Plan

| Field | Detail |
| --- | --- |
| Owner | [Your Name], AI/ML Engineer |
| Source Document | PHASE_2_IMPLEMENTATION_PLAN.md |
| Version | 1.0 |
| Date | 09 Oct 2026 |
| Total Steps | 37 (P2-01 … P2-37) |
| Duration | 6 weeks (Weeks 1–6) |
| Audience | AI/ML + Platform engineers, Engineering Manager, CTO |

## 0. How to Use This Plan

Steps are sequential within a week and partially parallel across tracks (see Section 5).

Every step follows the same rhythm: concept → build → test → done-when.

Each step must be runnable/testable on its own before the next begins.

"Done when" is the acceptance test — no step is complete without it passing.

Suggested cadence: implement one step, verify, then proceed (pair-mode: concept first).

Legend: Est. = engineer-days · Dep. = required prior steps · L# = Phase 2 layer · W# = week.

## 1. Prerequisites & Assumptions

Phase 1 complete (10/21 verified): intake → analyzer → researcher ⇄ critic → risk → approval → executor.

Paid Hosted API (Primary) + Local qwen2.5:7b via Ollama (Fallback); catalog + validator; interrupt() HITL; audit reducer.

Available: PostgreSQL 16, Redis 7, Docker (or Kubernetes), Slack workspace, SMTP, optional Twilio.

Assumption: production targets are Kubernetes-based (needed for Layer 5 canary).

## 2. Target Repository Layout

opsflow_ai/

├── app/                # Phase 1 agent core (state, graph, nodes, tools, catalog, safety)

├── api/                # NEW: FastAPI service (webhooks, approvals, health, metrics)

│   ├── main.py

│   ├── routes/         (webhooks.py, approvals.py, incidents.py)

│   ├── deps.py

│   └── security.py     (HMAC verification, auth)

├── worker/             # NEW: queue workers (alert processing, scheduled jobs)

│   ├── tasks.py

│   └── scheduler.py    (escalations, feedback loop)

├── db/                 # NEW: SQLAlchemy models + session

│   └── models.py

├── migrations/         # NEW: Alembic migrations

├── integrations/       # NEW: tenant_kb.py, slack.py, email.py, sms.py, prometheus.py

├── observability/      # NEW: tracing.py, metrics.py, logging.py

├── deploy/             # NEW: Dockerfile, docker-compose.yml, k8s/ (rollouts, analysis)

├── evals/              # NEW: dataset.jsonl, run_eval.py

├── tests/              # integration + unit tests

├── .env.example

├── PHASE_2_IMPLEMENTATION_PLAN.md

├── PHASE_2_BUILD_PLAN.md

└── requirements.txt

## 3. Build Tracks (Overview)

| Track | Layer | Steps | Theme |
| --- | --- | --- | --- |
| T1 | L1 | P2-01 … P2-09 | Event-driven ingestion + durable foundation |
| T2 | L2 | P2-10 … P2-15 | Multi-tenant knowledge + multi-source, high-confidence diagnosis |
| T3 | L3 | P2-16 … P2-21 | Sandboxed, auditable execution |
| T4 | L4 | P2-22 … P2-26 | Multi-channel approvals + escalation |
| T5 | L5 | P2-27 … P2-30 | Canary rollout + auto-rollback |
| T6 | L6/L7 | P2-31 … P2-37 | Observability, reporting, learning |

## 4. Step-by-Step Plan

### Week 1 — Foundation (T1)

#### P2-01 — Repo & local infrastructure setup

Build: Split app/ (agent core) from new api/, worker/, db/, integrations/, observability/, deploy/, evals/, tests/. Add docker-compose.yml (Postgres 16 + Redis 7). Extend config.py with DB/Redis/API settings.

Concept: service boundaries, 12-factor config, local-first dev.

Done when: docker compose up starts PG + Redis; python -c "import api.main, worker.tasks" succeeds.

Est: 0.5d · Dep: —

#### P2-02 — Database models & migrations

Build: SQLAlchemy models + Alembic migrations for processed_alerts, incidents, execution_logs, fix_outcomes (schemas in Implementation Plan, Appendix A).

Concept: schema-first, versioned migrations, JSONB for params/checks.

Done when: alembic upgrade head and downgrade run cleanly; all 4 tables exist.

Est: 1d · Dep: P2-01

#### P2-03 — FastAPI skeleton + structured logging

Build: api/main.py with /healthz, /readyz; Loguru/structlog JSON logs: timestamp, level, incident_id, stage, duration_ms, message.

Concept: structured logging, liveness/readiness probes.

Done when: app boots; /healthz → 200; emitted logs parse as JSON.

Est: 0.5d · Dep: P2-01

#### P2-04 — Durable checkpoints (PostgresSaver)

Build: Swap InMemorySaver → PostgresSaver behind CHECKPOINTER=postgres|memory; register custom state types in the checkpoint allowlist; manage setup/connection lifecycle.

Concept: durable execution, resumable workflows, checkpoint stores.

Done when: pause at approval, restart the API process, resume the same incident exactly once.

Est: 1d · Dep: P2-02

#### P2-05 — Webhook endpoint + HMAC verification

Build: POST /api/v1/webhooks/alert; read raw body; verify X-Signature via hmac.compare_digest with per-source secrets; return 202 / 401 / 400.

Concept: webhook authenticity, constant-time comparison, anti-spoofing.

Done when: valid signature → 202; tampered/unsigned → 401; malformed → 400.

Est: 1d · Dep: P2-03

#### P2-06 — Idempotency, normalization, dedupe

Build: Insert into processed_alerts (unique alertssignature); normalize to Alert schema; merge same `service + errorclass` within a 5-min window; promote severity to max.

Concept: idempotency keys, deduplication windows, alert storms.

Done when: replayed payload creates no new incident; a 500-alert burst for one service merges into one.

Est: 1d · Dep: P2-05

#### P2-07 — Rate limiting + severity classification

Build: Redis sliding-window limiter (50/min/service); rules-first severity classifier + LLM enrichment; critical triggers immediately, warning/info batched.

Concept: backpressure/throttling, rules-as-guardrails before ML.

Done when: 51st alert/min is throttled/coalesced; each alert is severity-labelled and stored.

Est: 1d · Dep: P2-06

#### P2-08 — Incident creation + queue worker

Build: background worker (RQ/Celery) consumes queued alerts, writes an incidents row, and invokes the LangGraph app with thread_id = incident_id using the Postgres checkpointer.

Concept: async decoupling (webhook fast-ack), worker idempotency, queue retries.

Done when: an alert produces an incident row + a graph run; worker restart does not duplicate work.

Est: 1d · Dep: P2-04, P2-07

#### P2-09 — Week 1 integration test (exit criteria)

Build: one script proving signed alert → dedupe → incident → graph → pause at approval → process restart → resume.

Done when: all Week 1 exit criteria pass in a single command.

Est: 0.5d · Dep: P2-08

### Week 2 — Enhanced Diagnosis (T2)

#### P2-10 — Multi-Tenant Knowledge Base Adapter & Tool

Build: Build an HTTP client/adapter for the Multi-Tenant RAG system. Support tenant-isolated namespaces for managed KB and live API connectors for external enterprise KBs. Implement the kb_search tool with a graceful fallback chain.

Concept: Multi-tenant RAG, namespace isolation, graceful degradation, zero-data-retention connectors.

Done when: a query correctly scopes to a specific tenant_id namespace, returns ranked runbook hits with citations, and gracefully falls back to web/history if the tenant KB is empty.

Est: 1.5d · Dep: P2-09

#### P2-11 — Historical incidents tool

Build: Postgres query for same service + error_class in the last 30 days; return the prior successful remediation + its success rate.

Concept: operational memory, pattern matching, closed-loop history.

Done when: a recurring signature surfaces the last successful fix.

Est: 1d · Dep: P2-02

#### P2-12 — Parallel research (Send Map-Reduce)

Build: replace the sequential researcher with a Send fan-out to 3 sub-agents (KB, web, history); merge with the existing operator.add reducer; fan-in to the critic.

Concept: LangGraph Map-Reduce (Send), fan-out/fan-in, reducer accumulation.

Done when: all 3 sources appear merged in state; wall-clock ~3× faster than sequential.

Est: 2d · Dep: P2-10, P2-11

#### P2-13 — Rubric confidence scoring

Build: weighted module → 0–100 from KB match, source agreement, history success rate, catalog match, critic score; persist a per-source breakdown.

Concept: evidence-based confidence vs self-reported scores.

Done when: every fix has a confidence + breakdown; < 70 is flagged for manual review.

Est: 1.5d · Dep: P2-12

#### P2-14 — History-aware proposal

Build: proposer suggests the proven fix first for recurring issues (with its success rate), while staying catalog-constrained.

Concept: learning from past fixes, preference ordering.

Done when: a recurrence prefers the previously successful remediation.

Est: 1d · Dep: P2-11, P2-13

#### P2-15 — Week 2 integration test (exit criteria)

Build: end-to-end diagnosis with 3 sources + rubric confidence + history-aware proposal.

Done when: all Week 2 exit criteria pass.

Est: 0.5d · Dep: P2-14

### Week 3 — Safe Execution (T3)

#### P2-16 — Sandbox executor (isolation)

Build: runner abstraction applying the catalog fix in an ephemeral Docker/K8s pod; argv + shell=False, timeout, resource limits, restricted env; no production credentials.

Concept: blast-radius isolation, least privilege, ephemeral environments.

Done when: a fix executes only inside the sandbox; production is untouched.

Est: 2d · Dep: P2-09

#### P2-17 — Sandbox validation suite

Build: health checks + smoke tests + assertions after the fix; capture results as sandbox_checks JSON.

Concept: verification gates, test-as-a-barrier.

Done when: pass/fail is recorded; a failing validation blocks promotion.

Est: 1.5d · Dep: P2-16

#### P2-18 — Automatic rollback

Build: pre-fix snapshot; on validation failure auto-revert; enforce a mandatory rollback plan for irreversible actions.

Concept: idempotent revert, safety invariants.

Done when: a failed validation reverts the sandbox cleanly.

Est: 1.5d · Dep: P2-17

#### P2-19 — Execution audit trail

Build: write execution_logs (who/what/when/where/result); append-only; queryable by incident.

Concept: immutable audit, compliance-ready records.

Done when: every execution attempt is audited end-to-end.

Est: 1d · Dep: P2-16

#### P2-20 — Self-correction on sandbox failure

Build: a failed sandbox result loops back to the proposer with failure feedback (reuse the critic loop + cap).

Concept: feedback into the decision, bounded retries.

Done when: a failed fix triggers the next candidate automatically.

Est: 1d · Dep: P2-18

#### P2-21 — Week 3 integration test (exit criteria)

Build: proposal → approval → sandbox → validate → "approve for production"; audit verified.

Done when: all Week 3 exit criteria pass.

Est: 0.5d · Dep: P2-20

### Week 4 — Notifications (T4)

#### P2-22 — Approval service + resume endpoint

Build: POST /api/v1/approvals/{thread_id} loads the graph with the Postgres checkpointer and calls Command(resume={approved, approver}); idempotent.

Concept: resuming a paused graph from an external channel.

Done when: an API call resumes the correct paused incident exactly once.

Est: 1d · Dep: P2-04

#### P2-23 — Slack integration

Build: Slack app posting a Block Kit message (incident, root cause, fix, sandbox result) with [Approve for Production] [Reject] [View Details]; verify Slack interactive payload signatures; call the resume endpoint.

Concept: interactive approvals, signed callbacks.

Done when: a button click resumes the correct incident.

Est: 2d · Dep: P2-22

#### P2-24 — Email backup channel

Build: SMTP with signed, time-limited approve/reject links for approvers not on Slack.

Concept: fallback channels, signed tokens.

Done when: an email link approves/rejects the incident.

Est: 1d · Dep: P2-22

#### P2-25 — SMS/PagerDuty + escalation policy

Build: critical-only SMS at 15 min; escalation scheduler (30 min → manager → senior → CTO) via delayed jobs.

Concept: on-call escalation, SLA timers.

Done when: an unapproved critical incident escalates on schedule.

Est: 1.5d · Dep: P2-23

#### P2-26 — Week 4 integration test (exit criteria)

Build: approve via Slack, reject via email, escalate a critical incident.

Done when: all Week 4 exit criteria pass.

Est: 0.5d · Dep: P2-25

### Week 5 — Canary Deployment (T5)

#### P2-27 — Kubernetes + Argo Rollouts setup

Build: cluster manifests; install Argo Rollouts; author a Rollout CRD for the target service.

Concept: progressive delivery primitives.

Done when: the Rollout CRD applies and defines canary steps.

Est: 2d · Dep: P2-21

#### P2-28 — Prometheus analysis gates

Build: AnalysisTemplate on error rate, p95/p99 latency, HTTP 5xx, CPU/memory; gates at each step.

Concept: metric-driven promotion gates.

Done when: an unhealthy canary fails the gate automatically.

Est: 1.5d · Dep: P2-27

#### P2-29 — Progressive delivery + auto-rollback

Build: orchestrate 10→25→50→100% with monitoring windows; auto-rollback if error rate > 5%; route the rollback alert back through the webhook.

Concept: blast-radius control, closed-loop rollback.

Done when: a failing canary auto-rolls back; a healthy canary completes unattended.

Est: 2d · Dep: P2-28

#### P2-30 — Week 5 integration test (exit criteria)

Build: kind/minikube tests for both healthy and failing rollouts.

Done when: all Week 5 exit criteria pass.

Est: 1d · Dep: P2-29

### Week 6 — Observability, Reporting & Learning (T6)

#### P2-31 — OpenTelemetry tracing

Build: instrument graph, queue, and executors; propagate incident_id/trace context; export to Jaeger.

Concept: distributed tracing, span-per-stage.

Done when: one incident produces a single trace covering all stages.

Est: 2d · Dep: P2-30

#### P2-32 — Prometheus metrics + Grafana dashboards

Build: emit counters/histograms: incident_total, incident_auto_resolved_total, incident_manual_approval_total, mttd_seconds, mttr_seconds, fix_success_rate, sandbox_failures_total, canary_rollback_total, approval_latency_seconds; build dashboards.

Concept: SLO/observability instrumentation.

Done when: dashboards show live KPI values.

Est: 1.5d · Dep: P2-31

#### P2-33 — Structured logging pipeline

Build: JSON logs correlated by incident_id, ELK-ready; consistent fields across services.

Concept: observability via logs, correlation IDs.

Done when: logs parse and are queryable by incident.

Est: 1d · Dep: P2-03

#### P2-34 — Post-incident report generator

Build: auto-generate Markdown/PDF with timeline, root cause, fix applied, impact, lessons learned; link to the incident.

Concept: automated retrospectives, knowledge capture.

Done when: a report is generated ≤ 60 s after resolution.

Est: 1.5d · Dep: P2-19, P2-32

#### P2-35 — Feedback loop + fix_outcomes

Build: T+24h (and T+1h for critical) stability check; write fix_outcomes; mark stable/unstable.

Concept: closed-loop learning, delayed verification.

Done when: outcomes are recorded automatically for every applied fix.

Est: 1d · Dep: P2-19

#### P2-36 — Confidence calibration + eval harness in CI

Build: recalibrate rubric weights from outcomes; golden incident set replayed in CI; gate on correct-remediation % and false-safe rate = 0.

Concept: continuous evaluation, calibration error.

Done when: CI eval is green and calibration error trends down.

Est: 2d · Dep: P2-35

#### P2-37 — End-to-end acceptance + go-live

Build: full drill (alert → diagnosis → sandbox → Slack approval → canary → report); operational runbook; go-live checklist.

Concept: production readiness, operational handover.

Done when: the Phase 2 Definition of Done (Section 8) is fully met.

Est: 1.5d · Dep: P2-36

## 5. Dependency & Sequencing Notes

Critical path: P2-01 → P2-02 → P2-04 → P2-08 → P2-12 → P2-16 → P2-22 → P2-27 → P2-31 → P2-37.

Parallelizable early: P2-10/P2-11 (integrations) can proceed once P2-02 lands, in parallel with P2-05…P2-08.

Parallelizable mid: P2-16…P2-21 (sandbox) and P2-22…P2-26 (notifications) can run as two workstreams.

Hard prerequisites: P2-04 (durable state) before any approval/resume work; P2-27 (K8s) before canary; P2-31/P2-32 before P2-34.

Estimated total: ~47 engineer-days; achievable in 6 weeks with 2 engineers (or 1 engineer + AI-assisted development).

## 6. Requirements Traceability Matrix

| Phase 2 Requirement | Step(s) |
| --- | --- |
| FastAPI webhook endpoint | P2-05 |
| HMAC-SHA256 signature verification | P2-05, P2-23 |
| Idempotency keys (processed_alerts) | P2-06 |
| Alert dedupe / merge | P2-06 |
| Rate limiting (50/min/service) | P2-07 |
| AI severity classification | P2-07 |
| Multi-Tenant Internal Knowledge Base (RAG) | P2-10 |
| Parallel multi-agent research (Map-Reduce) | P2-12 |
| Confidence scoring (rubric) | P2-13 |
| Historical pattern matching | P2-11, P2-14 |
| PostgresSaver durable checkpoints | P2-04 |
| Sandboxed execution | P2-16 |
| Sandbox validation tests | P2-17 |
| Automatic rollback (sandbox) | P2-18 |
| Execution audit trail (execution_logs) | P2-19 |
| Slack interactive approvals | P2-23 |
| Email backup channel | P2-24 |
| SMS / PagerDuty (critical) | P2-25 |
| Escalation policies | P2-25 |
| Canary rollout (Argo/Flagger) | P2-27, P2-29 |
| Automatic canary rollback | P2-29 |
| Progressive delivery 10→100% | P2-29 |
| OpenTelemetry tracing | P2-31 |
| Prometheus metrics + Grafana | P2-32 |
| Structured JSON logging (ELK) | P2-33 |
| Post-incident auto reports | P2-34 |
| Feedback loop (fix_outcomes) | P2-35 |
| Learning from past fixes | P2-14, P2-35 |
| Confidence calibration | P2-36 |
| Eval harness (false-safe = 0) | P2-36 |

## 7. Cross-Cutting Concerns

Security: HMAC on all inbound webhooks (P2-05), signed Slack callbacks (P2-23), sandbox with no prod credentials (P2-16), redaction retained from Phase 1.

Testing: each step ships its own acceptance test; weekly integration gates at P2-09, P2-15, P2-21, P2-26, P2-30, P2-37.

Configuration: all new settings in config.py + .env.example (DB, Redis, Slack, SMTP, Twilio, checkpointer flag, HMAC secrets).

Backward compatibility: Phase 1 CLI remains functional; new features behind flags so local demo still works.

CI/CD: lint + unit + integration + eval (P2-36) on every change.

## 8. Definition of Done

Per step: builds; acceptance test passes; no regression in Phase 1 tests; config documented; logged/traced where applicable.

Per week: the week's integration test passes; deliverable demoed; exit criteria signed off.

Program (Phase 2 complete):

MTTD ≈ 0 s and MTTR ≤ 15 min measured in production.

≥ 70% of qualifying incidents auto-resolved.

0 production incidents caused by an OpsFlow-applied fix.

100% of incidents fully traced and audited; approvals durable across restarts.

Eval harness green in CI (false-safe rate = 0).

## 9. Immediate Next Action

Start P2-01 (repo & local infrastructure setup), then P2-02 (DB models/migrations) and P2-03 (FastAPI skeleton).

Decisions needed first:

Canary platform: Argo Rollouts vs Flagger → recommend Argo Rollouts.

Sandbox isolation: Docker-in-Docker vs ephemeral K8s pods → recommend K8s pods.

Inference at scale — DECIDED: paid hosted API for dev/demo, local Ollama as fallback.

Approval SLA + escalation tree owners → confirm policy.

Prepared by [Your Name], AI/ML Engineer · OpsFlow AI Phase 2 Build Plan · 09 Oct 2026